## OERFSJ Task List
OERFSJ Task List
Gap Analysis
Task | Deliverable | Assigned to | Due Date | Completed (X) | Notes
Assessment: Faculty Confidence Survey | Faculty Confidence Survey | OER Team | 2023-07-23
Attend summer workshops |  | OER Team | 2023-08-04
Basic copyright training |  | OER Team
Research and identify relevant OER | Gap Analysis Worksheet | OER Team | 2023-12-18
Evaluate identified OER w/rubric | Gap Analysis Worksheet/OERFSJ Rubric | OER Team | 2023-12-18
Consultation w/OER Librarian and OER Liaison |  | OER Team | 2023-08-31
Define project scope/goals | Year 2 Project Plan | OER Team | 2023-12-18
Reflect & Rest | Nothing | All
Pre-production & Design
Task | Deliverable | Assigned to | Due Date | Completed (X) | Notes
Review & revise project scope |  | OER Team
Curate existing OER | Resource Adaptation Guide (2nd tab in this workbook) | OER Team
Evaluate licensing of third party works to be used | Resource Adaptation Guide (2nd tab in this workbook) | OER Team
Create working documents | Collaborative workspace & storage | OER Team
Establish development timeline/scope
Create assessment plan
Draft sustainability plan | Sustainability Plan
Outline OER
Select styleguide
Call for volunteers to contribute content (if applicable)
Select publishing platform and tool(s) | Tool Parade
Learn relevant tools
Accessibility/UDL training | Accessibility/UDL workshop
Reflect & Rest | Nothing | All
Development
Task | Deliverable | Assigned to | Due Date | Completed (X) | Notes
Remain mindful of DEIA
Write content
Revise content (team members review)
Develop open pedagogy elements/course assignments
Develop interactive pedagogical elements
Develop field test
Conduct field test
Analyze and implement field test results
Upload content to tool/platform
Tool/platform: Select format & style
Tool/platform: Consider graphic design
Tool/platform: Consider cover design
Develop frontmatter: author profiles, introduction, copyright statement
Submit content to copy editor
Submit for copyright check |  | OER Librarian & Liaison/ETE
Submit for IP/Accessibility/UDL Check |  | OER Librarian & Liaison/ETE
Identify external reviewers and conduct peer review
Implement peer reviewer's external feedback
Revise or pilot assessment plan for OER
Complete Year 2 Annual Report | Year 2 Annual Report | OER Team | 2024-12-16
Reflect & Rest | Nothing | All
Publication & Dissemination
Task | Deliverable | Assigned to | Due Date | Completion Date
Assess OER with OERFSJ Rubric | OERFSJ Rubric | OER Team
Marketing: write book description/abstract and author profiles
Publish OER | Your OER
Integrate into designated course
Deploy assessment plan for OER
Revise OER
Disseminate and share via OER networks
Establish error reporting protocol
Establish adaptation reporting
Establish practice for updating OER
Year 3 Annual Report | Year 3 Annual Report | OER Team | 2025-12-19
Assessment: Faculty Confidence Survey | Faculty Confidence Survey |  | 2025-12-19
Reflect & Rest | Nothing | All

## Resource Adaptation Guide
Resource Adaptation Guide
Course Objective | Resource Title/Link | Original Platform | Format(s) Available
Example: CO #1, 2 | Principles of Macroeconomics | OpenStax | Html, pdf

## Codebook
Concept | Variable | Meaning | Notes
Grant program | OERFSJ | Open Educational Resources for Social Justice
Participating recipients | OER Team | OER Faculty Grant Recipient Team
Open Education components | OER | Open Educaional Resources
SOURCES: "OERFSJ Task List" by Loyolay Marymount University's OER for Social Justice was adapted from "Production of OER" by Billy Meinke and "Project Timeline (in depth) by Anita Walz under a CC BY 4.0. International license. CC BY 4.0. "Resource Adaptation Guide" by Abbey Elder, updated May 2020, licensed CC BY 4.0, was adapted from "Project Plan Template" by Sara Davis, Amanda Larson, and Julie Lang, licensed CC BY 4.0.