## OER Objectives Worksheet
Step 1: List your course outcomes | Step 2: List and revise your weekly or module objectives
Course Outcomes | Week or Module | Original Weekly or Module Objectives | Measurable Weekly or Module Objectives
CO-1 Create a DEIA-infused OER | Module 1 | Create a list of measurable objectives. | Create a list of measurable course module/weekly objectives on which OER content creation will be based. | Completed OER FSJ Deliverables 1-5 by Theresa Huff is licensed under CC BY 4.0
CO-2 Create a content map for their OER |  | Create a Table of Contents | Organize objectives to be reached by topic
CO-3 Organize a project timeline with deliverables and assigned tasks |  |  | Organize topics and subtopics into chapters and sections of chapters
CO-4 Create interactive multimedia that support learning objectives |  |  | Assign chapter and section creation and adaption
CO-5 Apply Creative Commons licenses appropriately to adapted or created OER | Module 2 | Create a Content Map | Identify possible content resources for each adaption and creation to support reaching objectives
Identify possible aligned summative and formative assessments
Create a working To Do list for finding or creating content
| Module 3 | Create a Timeline | Create a working Timeline with deadlines, deliverables, and assigned tasks
|  | New, added objectives | Identify key principles and goals of DEIA
Adapt module/weekly objectives to include or infuse DEIA principles and goals
Track planned use of Images and Figures

## OER Objectives Organizer
Step 1: Organize your objectives |  |  | Step 2: Create a Table of Contents
Learning Objectives | Topics | Chapters | Chapter Title | Chapter Section | Learning Objectives Covered | Assigned To
Create a list of measurable course module/weekly objectives on which OER content creation will be based. | Objectives to Table of Contents | Planning your OER | 1. Planning Your OER | DEIA-infused Objectives | Identify key principles and goals of DEIA | Karna
Organize objectives to be reached by topic | Objectives to Table of Contents | Planning your OER |  | Objectives to Table of Contents | Create a list of measurable course module/weekly objectives on which OER content creation will be based. | Karna
Organize topics and subtopics into chapters and sections of chapters | Objectives to Table of Contents | Planning your OER |  |  | Adapt module/weekly objectives to include or infuse DEIA principles and goals | Theresa
Assign chapter and section creation and adaption | Objectives to Table of Contents | Planning your OER |  |  | Organize objectives to be reached by topic | Theresa
Identify possible content resources for each adaption and creation to support reaching objectives | Content and Assessment Mapping | Planning your OER |  |  | Organize topics and subtopics into chapters and sections of chapters | Theresa
Identify possible aligned summative and formative assessments | Content and Assessment Mapping | Planning your OER |  |  | Assign chapter and section creation and adaption | Theresa
Create a working To Do list for finding or creating content | Content and Assessment Mapping | Planning your OER |  | Content and Assessment Mapping | Identify possible content resources for each adaption and creation to support reaching objectives | Theresa
Create a working Timeline with deadlines, deliverables, and assigned tasks | Project Timeline | Planning your OER |  |  | Create a working To Do list for finding or creating content | Theresa
0 |  | Planning your OER |  |  | Identify possible aligned summative and formative assessments | Theresa
Identify key principles and goals of DEIA | DEIA-infused Objectives | Planning your OER |  | Images and Figures | Track planned use of Images and Figures | Karna
Adapt module/weekly objectives to include or infuse DEIA principles and goals | DEIA-infused Objectives | Planning your OER |  | Project Timeline | Create a working Timeline with deadlines, deliverables, and assigned tasks | Theresa
Track planned use of Images and Figures | Images and Figures | Planning your OER
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## OER Content and Assessment Map
Table of Contents |  |  |  | OER Content Map |  |  | OER Assessment Map
Chapter Title | Chapter Section | Learning Objectives Covered | Assigned To | I plan to… | Links I've found | To Do List | Summative Assessment | Formative Assessments/Interactivity | Links
1. Planning Your OER | DEIA-infused Objectives | Identify key principles and goals of DEIA | Karna | Adapt ch. 1 of a Pressbook with DEI, but add the anti-racism piece in. | https://openoregon.pressbooks.pub/dothework/ | 1. Clone the Pressbook 2. Annotate changes with team using Hypothes.is 3. Adapt/write chapter 1 | Deliverable 1 | H5P Hotspot of DEIA image in Section 1.2 H5P Drag-the-Words Self-Check at end of Section 1.2 | https://h5p.org/image-hotspots https://h5p.org/drag-the-words
0 | Objectives to Table of Contents | Create a list of measurable course module/weekly objectives on which OER content creation will be based. | Karna | Find examples of objectives before and after infusing DEIA principles |  | Write steps and rationale for infusing creating measurable objectives | Deliverable 1 | OER Objectives Worksheet Directions with examples OER Objectives Worksheet tab in OERFSJ Deliverables 1-5 spreadsheet
0 | 0 | Adapt module/weekly objectives to include or infuse DEIA principles and goals | Theresa | Adapt the backwards design model used for course mapping for OER creation | Course mapping tool | Write steps and rationale for infusing DEIA into objectives | Deliverable 1 | H5P Interactive Videos with Reflections in Section 1.2, 1.3, and 1.4 H5P Documentation for reflections in Section 1.3 and 1.4
0 | 0 | Organize objectives to be reached by topic | Theresa | Write this portion based on Karna's adaption of Ch. 1 |  | Write steps for organizing objectives into topics | Deliverable 2 | OER Objectives Organizer Directions with examples OER Objectives Organizer tab in OERFSJ Deliverables 1-5 spreadsheet
0 | 0 | Organize topics and subtopics into chapters and sections of chapters | Theresa | Write the guidance and rationale and test it with our own OER creation plan. |  | Write steps for organizing topics into chapters | Deliverable 2 | OER Objectives Organizer Directions with examples OER Objectives Organizer tab in OERFSJ Deliverables 1-5 spreadsheet
0 | 0 | Assign chapter and section creation and adaption | Theresa | Write the guidance and test it with our own OER creation plan. |  | Write steps and rationale for assigning sections and chapters | Deliverable 2 | OER Objectives Organizer Directions with examples OER Objectives Organizer tab in OERFSJ Deliverables 1-5 spreadsheet
0 | Content and Assessment Mapping | Identify possible content resources for each adaption and creation to support reaching objectives | Theresa | Write the guidance and test it with our own OER creation plan. |  | Write steps and rationale for mapping content | Deliverable 3 | OER Content and Assessment Map Directions with examples OER Content and Assessment Map tab in OER FSJ Deliverables 1-5 spreadsheet
0 | 0 | Create a working To Do list for finding or creating content | Theresa | Modify the course mapping tool for OER creation |  | Write steps and rationale creating To Do lists | Deliverable 3 | OER Content and Assessment Map Directions with examples OER Content and Assessment Map tab in OER FSJ Deliverables 1-5 spreadsheet
0 | 0 | Identify possible aligned summative and formative assessments | Theresa | Modify the course mapping tool for OER creation |  | Write steps and rationale for mapping assessments | Deliverable 4 | OER Content and Assessment Map Directions with examples OER Content and Assessment Map tab in OER FSJ Deliverables 1-5 spreadsheet
0 | Images and Figures | Track planned use of Images and Figures | Karna | Modify the course mapping tool for OER creation |  | Write steps and rationale for tracking images and figures | TBD | OER Images and Figures Directions with examples OER Images and Figures tab in OERFSJ Deliverables 1-5 spreadsheet
0 | Project Timeline | Create a working Timeline with deadlines, deliverables, and assigned tasks | Theresa | Adapt the OERFSJ Gap Analysis tool |  | Write steps and rationale for creating a project timeline | Deliverable 5 | OER Project Timeline Directions and examples OER Project Timeline tab in OERFSJ Deliverables 1-5 spreadsheet
0 | 0 | 0 | 0 | Modify project management guidance and test it.
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0

## OER Images and Figures
Table of Contents |  |  |  | OER Images and Figures
Chapter Title | Chapter Section | Learning Objectives Covered | Assigned To | Title | Author | Source | License
1. Planning Your OER | DEIA-infused Objectives | Identify key principles and goals of DEIA | Karna
0 | Objectives to Table of Contents | Create a list of measurable course module/weekly objectives on which OER content creation will be based. | Karna | Measurable Learning Objectives | Instructional Technology at Mount St. Joseph | https://www.youtube.com/watch?v=n8___eBU9t8 | Undisclosed; will embed in page
0 | 0 | Adapt module/weekly objectives to include or infuse DEIA principles and goals | Theresa
0 | 0 | Organize objectives to be reached by topic | Theresa
0 | 0 | Organize topics and subtopics into chapters and sections of chapters | Theresa
0 | 0 | Assign chapter and section creation and adaption | Theresa
0 | Content and Assessment Mapping | Identify possible content resources for each adaption and creation to support reaching objectives | Theresa
0 | 0 | Create a working To Do list for finding or creating content | Theresa
0 | 0 | Identify possible aligned summative and formative assessments | Theresa
0 | Images and Figures | Track planned use of Images and Figures | Karna
0 | Project Timeline | Create a working Timeline with deadlines, deliverables, and assigned tasks | Theresa
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0

## OER Project Timeline
OER Project Timeline
Due Date | Deliverable | Assigned To | Done!
2024-06-01
2024-07-01
2024-08-01
2024-09-01
2024-10-01
2024-11-01
2024-12-01
2025-01-01
2025-02-01
2025-03-01
2025-04-01
2025-05-01
2025-06-01
2025-07-01
2025-08-01
2025-09-01
2025-10-01
2025-11-01
2025-12-01
2026-01-01

## Sample Individual Timeline
Sample Individual Project Timeline
Due Date | My Deliverables | From Chapter/Section | Done!
2024-06-01
2024-07-01
2024-08-01
2024-09-01
2024-10-01
2024-11-01
2024-12-01
2025-01-01
2025-02-01
2025-03-01
2025-04-01
2025-05-01
2025-06-01
2025-07-01
2025-08-01
2025-09-01
2025-10-01
2025-11-01
2025-12-01
2026-01-01